## Recap
Avancement | 98.77%

## liste des taches
Module | Nom page / Fichier | Description | Type | Estimation | Temps passé | Reste à faire | Avancement | Qui | Status
Migrations | CreateRhSchema.php | Table departements | Base | 10 | 0 | 10 | 100% | duo | OK
Migrations | CreateRhSchema.php | Table employees | Base | 10 | 10 | 0 | 100% | duo | OK
Migrations | CreateRhSchema.php | Table types_conge | Base | 10 | 10 | 0 | 100% | duo | OK
Migrations | CreateRhSchema.php | Table soldes | Base | 10 | 10 | 0 | 100% | duo | OK
Migrations | CreateRhSchema.php | Table conges | Base | 10 | 10 | 0 | 100% | duo | OK
Seeders | RhSeeder.php | 3 départements | Base | 5 | 5 | 0 | 100% | duo | OK
Seeders | RhSeeder.php | 4 employés | Base | 5 | 5 | 0 | 100% | duo | OK
Seeders | RhSeeder.php | 4 types de congé | Base | 5 | 5 | 0 | 100% | duo | OK
Seeders | RhSeeder.php | 7 soldes 2025/2026 | Base | 5 | 5 | 0 | 100% | duo | OK
Seeders | RhSeeder.php | 10 demandes historique | Base | 5 | 5 | 0 | 100% | duo | OK
Config | Database.php | SQLite3 + RH.db racine | Config | 10 | 10 | 0 | 100% | duo | OK
Models | EmployeeModel.php | Auth + hashPassword hook | Modèle | 20 | 20 | 0 | 100% | Ny Aina | OK
Models | DepartmentModel.php | CRUD basique | Modèle | 10 | 10 | 0 | 100% | Harena | OK
Models | LeaveTypeModel.php | Gestion types de congé | Modèle | 10 | 10 | 0 | 100% | Harena | OK
Models | LeaveBalanceModel.php | Suivi soldes par année | Modèle | 15 | 15 | 0 | 100% | Harena | OK
Models | LeaveRequestModel.php | Gestion demandes | Modèle | 15 | 15 | 0 | 100% | Ny Aina | OK
Auth | AuthController.php | login() - formulaire | Controller | 15 | 15 | 0 | 100% | Ny Aina | OK
Auth | AuthController.php | attemptLogin() - session | Controller | 20 | 20 | 0 | 100% | Ny Aina | OK
Auth | AuthController.php | logout() | Controller | 5 | 5 | 0 | 100% | Ny Aina | OK
Employé | EmployeeController.php | dashboard() stats+soldes | Controller | 30 | 30 | 0 | 100% | Harena | OK
Employé | EmployeeController.php | index() historique demandes | Controller | 20 | 20 | 0 | 100% | Harena | OK
Employé | EmployeeController.php | create() formulaire | Controller | 20 | 20 | 0 | 100% | Harena | OK
Employé | EmployeeController.php | store() + validation solde | Controller | 30 | 30 | 0 | 100% | Harena | OK
RH | RhController.php | dashboard() en attente | Controller | 20 | 20 | 0 | 100% | Ny Aina | OK
RH | RhController.php | index() toutes demandes | Controller | 15 | 15 | 0 | 100% | Ny Aina | OK
RH | RhController.php | approve() + MAJ solde | Controller | 30 | 30 | 0 | 100% | Ny Aina | OK
RH | RhController.php | refuse() | Controller | 15 | 15 | 0 | 100% | Ny Aina | OK
Admin | AdminController.php | dashboard() stats globales | Controller | 20 | 20 | 0 | 100% | Harena | OK
Admin | AdminController.php | employees() CRUD | Controller | 30 | 30 | 0 | 100% | Harena | OK
Admin | AdminController.php | departements() CRUD | Controller | 20 | 20 | 0 | 100% | Harena | OK
Admin | AdminController.php | typesConge() CRUD | Controller | 20 | 20 | 0 | 100% | Harena | OK
Vues | layouts/auth.php | Layout connexion | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | layouts/app.php | Layout sidebar+topbar | Vue | 20 | 20 | 0 | 100% | duo | OK
Vues | auth/login.php | Formulaire connexion | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | employee/dashboard.php | Dashboard soldes+demandes | Vue | 20 | 20 | 0 | 100% | duo | OK
Vues | employee/index.php | Historique demandes | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | employee/create.php | Formulaire création | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | rh/dashboard.php | Demandes en attente | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | rh/index.php | Toutes les demandes | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | admin/dashboard.php | Stats globales | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | admin/employes.php | CRUD employés | Vue | 20 | 20 | 0 | 100% | duo | OK
Vues | admin/departements.php | CRUD départements | Vue | 15 | 15 | 0 | 100% | duo | OK
Vues | admin/types_conge.php | CRUD types de congé | Vue | 15 | 15 | 0 | 100% | duo | OK
Sécurité | AuthFilter.php | Middleware auth + rôle | Filtre | 20 | 20 | 0 | 100% | Ny Aina | OK
Sécurité | Filters.php | CSRF global + alias auth | Config | 10 | 10 | 0 | 100% | Ny Aina | OK
Routes | Routes.php | GET / → Home redirect | Route | 5 | 5 | 0 | 100% | Harena | OK
Routes | Routes.php | GET/POST /login + /logout | Route | 5 | 5 | 0 | 100% | Harena | OK
Routes | Routes.php | Groupe employee (4 routes) | Route | 10 | 10 | 0 | 100% | Harena | OK
Routes | Routes.php | Groupe rh (4 routes) | Route | 10 | 10 | 0 | 100% | Harena | OK
Routes | Routes.php | Groupe admin (6 routes) | Route | 10 | 10 | 0 | 100% | Harena | OK
Employé | EmployeeController.php | cancel() annuler demande en_attente | Controller | 15 | 15 | 0 | 100% | Ny Aina | OK
Employé | employee/index.php | Bouton annuler sur vue | Vue | 10 | 10 | 0 | 100% | Ny Aina | OK
Admin | AdminController.php | initSolde() initialiser solde annuel | Controller | 20 | 20 | 0 | 100% | Ny Aina | OK
Doc | README.md | Instructions install + comptes test | Doc | 20 | 20 | 0 | 100% | Harena | OK
Assets | chart.umd.min.js | Chart.js offline | Tâche | 10 | 10 | 0 | 100% | tous | OK
Assets | index.global.min.js | FullCalendar offline | Tâche | 10 | 10 | 0 | 100% | tous | OK
Admin | AdminController.php | Graphiques congés par mois/jour | Feature | 20 | 20 | 0 | 100% | tous | OK
Admin | dashboard.php | Graphiques mensuel + hebdo offline | Feature | 20 | 20 | 0 | 100% | tous | OK
Employee | EmployeeController.php | Demandes employé + events calendrier | Feature | 20 | 20 | 0 | 100% | tous | OK
Employee | dashboard.php | Calendrier + histogramme offline | Feature | 15 | 15 | 0 | 100% | tous | OK
UI | dashboard.php | Graphiques responsive mobile | Improvement | 15 | 15 | 0 | 100% | tous | OK
UI | dashboard.php | Dashboard admin responsive | Improvement | 15 | 15 | 0 | 100% | tous | OK
Performance | AdminController.php / Employee | Optimiser requêtes SQL GROUP BY | Improvement | 5 | 5 | 0 | 100% | tous | OK
Tests | repo | Tests visuels + unitaires graphiques | Task | 5 | 5 | 0 | 100% | tous | OK

## avancement projet
estimation total | temps passé total | reste à faire total | avancement | dépassement
815 | 805 | 10 | 98.77% | 0%
heure

## detail
Ligne | Total
1 | 0
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0
21 | 0
22 | 0
23 | 0
24 | 0
25 | 0
26 | 0
27 | 0
28 | 0
29 | 0
30 | 0
31 | 0
32 | 0
33 | 0
34 | 0
35 | 0
36 | 0
37 | 0
38 | 0
39 | 0
40 | 0
41 | 0
42 | 0
43 | 0
44 | 0
45 | 0
46 | 0
47 | 0
48 | 0
49 | 0
50 | 0
51 | 0
52 | 0
53 | 0
54 | 0
55 | 0
56 | 0
57 | 0
58 | 0
59 | 0
60 | 0
61 | 0
62 | 0
63 | 0
64 | 0
65 | 0
66 | 0
67 | 0